## How to Use This
12-Week Book Marketing Timeline
A week-by-week planner covering pre-launch, launch week, and the four weeks after — the period most authors under-plan for.
How This Spreadsheet Is Organized
— The "Timeline" tab covers Weeks -8 through +4 relative to your launch date (Week 0).
— Each row is one task, with columns for the responsible person, status, and notes.
— Tasks are grouped by phase — Pre-Launch, Launch Week, and Post-Launch — color-coded so you can see your current phase at a glance.
How to Use It
— Enter your actual launch date in the "Timeline" tab, cell B1 — every week label updates relative to it automatically.
— Update the Status column as you go: Not Started, In Progress, Done, or Blocked.
— Add or remove rows freely — this is a starting structure, not a fixed list. Every book's marketing plan looks a little different.
— Assign an Owner to each task, even if that's just your own name or "Collingwood Press" for tasks we're handling on your behalf.
Need Help Executing This Plan?
— Collingwood Press's marketing team can run this entire timeline for you — Amazon optimization, social campaigns, and review outreach. Visit thecollingwoodpress.com or email info@thecollingwoodpress.com.

## Timeline
Launch Date: | 2026-10-08 | ← Enter your real launch date here
Week | Phase | Task | Owner | Status | Notes
2026-08-13 | Pre-Launch | Finalize manuscript, cover, and back-cover copy |  | Not Started
2026-08-13 | Pre-Launch | Set up or update your author website and email list signup |  | Not Started
2026-08-20 | Pre-Launch | Identify 15-20 book bloggers/reviewers in your genre |  | Not Started
2026-08-20 | Pre-Launch | Order/request Advance Reader Copies (ARCs) or ARC eBook files |  | Not Started
2026-08-27 | Pre-Launch | Send ARCs to reviewers with a clear, polite deadline |  | Not Started
2026-08-27 | Pre-Launch | Draft your Amazon/retailer book description and keywords |  | Not Started
2026-09-03 | Pre-Launch | Set up Amazon Author Central / retailer author profiles |  | Not Started
2026-09-03 | Pre-Launch | Plan your launch week social content calendar |  | Not Started
2026-09-10 | Pre-Launch | Reach out to podcasts or newsletters for launch-week features |  | Not Started
2026-09-10 | Pre-Launch | Announce cover reveal to your email list and social channels |  | Not Started
2026-09-17 | Pre-Launch | Confirm pre-order links are live on all retailers |  | Not Started
2026-09-17 | Pre-Launch | Begin countdown content: excerpts, behind-the-scenes posts |  | Not Started
2026-09-24 | Pre-Launch | Follow up with reviewers who haven't yet posted |  | Not Started
2026-09-24 | Pre-Launch | Finalize launch-day email to your list |  | Not Started
2026-10-01 | Pre-Launch | Schedule all launch-day social posts in advance |  | Not Started
2026-10-01 | Pre-Launch | Remind your personal network — friends, family, colleagues |  | Not Started
2026-10-08 | Launch Week | Publish/release the book across all retailers |  | Not Started
2026-10-08 | Launch Week | Send launch-day email to your list |  | Not Started
2026-10-08 | Launch Week | Post launch announcement across all social channels |  | Not Started
2026-10-08 | Launch Week | Ask early readers to leave a review in the first 48 hours |  | Not Started
2026-10-15 | Post-Launch | Monitor keyword rankings and adjust Amazon metadata if needed |  | Not Started
2026-10-15 | Post-Launch | Share early reader reactions and reviews on social media |  | Not Started
2026-10-22 | Post-Launch | Pitch local media, bookstores, or libraries for events |  | Not Started
2026-10-29 | Post-Launch | Evaluate ad spend results if running Amazon/social ads |  | Not Started
2026-11-05 | Post-Launch | Plan next-phase marketing: sequel teasers, box sets, or promotions |  | Not Started
Legend:
Pre-Launch
Launch Week
Post-Launch